## Risks Registry June 2017 (2) (hidden)
| MINISTRY OF REGIONAL DEVELOPMENT, PUBLIC ADMINISTRATION AND EUROPEAN FUNDS MA Black Sea Basin Unit |  | OPERATIONAL PROCEDURE |  |  |  | Code: PO.DAM-PCTE.BMN.11
[7 empty] | Edition I |  |  | Revision 0
|  |  | Procedure for risk management and identification of antifraud measures for the Joint Operational Programme Black Sea Basin 2014-2020 |  |  |  | Page 1
Risk register - Joint Operational Programme Black Sea Basin 2014-2020
Date of issue: …….06.2017
No. crt. | Category | Objectives/activities | Description of risk and its impact | Date of identification | Who identified (structure) | Causes | Inherent risk |  |  |  | Preventive actions | Residual risk |  |  |  | Responsible person / structure | Deadline | Status of implementation | Active / solved / inactive risk
[7 empty] | Probability | Impact | Control capacity | Global risk evaluation (R) |  | Probability | Impact | Control capacity | Global risk evaluation (R)
[7 empty] | P | I | C | R=IxP/C |  | P | I | C | R=IxP/C
I | Programme implementation risks | JOP includes all eligible countries | Lack of political commitment by some eligible countries to participate in the BSB programme | 2015 | Joint Programming Committee (JPC) | Political context | 3 | 2 | 1 | 6 | The programme is still presented for adoption by the EC and will only be implemented in those countries which have made the necessary formal commitment. | 1 | 2 | 1 | 2 | MA, JPC, EC | 2015-06-01 | The programme was adopted by the EC in December 2015 and it is implemented in those countries which have made the necessary formal commitment (Armenia, Bulgaria, Georgia, Greece, Republic of Moldova, Romania, Turkey, Ukraine). Azerbaijan and the Russian Federation have not confirmed their participation in the programme at the date of submission of the programme to the EC. | Solved
| Programme implementation risks | Programme strategic objectives in JOP are achieved | Cross-border cooperation is hampered by an unstable political situation in some regions and/or by regional conflicts | 2015 | JPC | Political context | 3 | 2 | 1 | 6 | Eligibility of some regions may be suspended, transfer of funds to some regions may be suspended. | 3 | 2 | 1 | 6 | EC, MA, NA | permanent | The Guidelines for Grant Applicants published for the first call for proposals in January 2017 specifies the eligible regions, referring to the EU restrictions on cooperation in some regions of Ukraine (Sevastopol and Crimea Republic), as provided for in the ENI CBC Programming document. | Active
| Programme implementation risks | Programme strategic objectives in JOP are achieved | EU sluggish growth and continuing problems emanating from the debt crisis limit further economic recovery in BSB and development of business and entrepreneurship | 2015 | JPC | Economic difficulties at EU/international level | 2 | 1 | 1 | 2 | Monitoring of the economic context at EU / international level in order to be able to intervene in case of difficulties | 2 | 1 | 1 | 2 | MA, NA, EC | permanent |  | Active
| Programme implementation risks | Programme launching is developed in an efficient and timely manner and all programme structures and procedures are adequately set up; Programme is implemented in accordance with deadlines set for each stage | ENI CBC new management and implementation modalities result in delays in programme start-up and implementation | 2015 | JPC | Differencies in ENI CBC legal framework, as compared with the ENPI CBC one | 3 | 2 | 2 | 3 | Identify potential bottlenecks, then enhance capacity, ensure sufficient resources and/or support adaptation of procedures as needed to speed up programme implementation. | 3 | 2 | 2 | 3 | AA, JMC, MA, JTS, NA, EC | permanent | Programme start-up: Preparatory actions required to start the programme: - establishment by the participating countries of the MA in July 2013 and of the JTS in September 2014; - JMC set up and first meeting in March 2016; - launching of the first call for proposals with a suspension clause linked to the entry into force of the financing agreements, in January 2017. MA designation activities: - The MA, with the support of EU funded project TESIM (Technical support to the implementation and management of ENI CBC programme) and of the National Authorities, elaborated the Description of Management and Control Systems (DMCS) for the programme, between 2016-2017, and submitted it to the Audit Authority in April 2017. Currently, the DMCS is under verification by the Audit Authority. Implementation: - trainings delivered to potential applicants under the first call for proposals about the programme rules and the draft guidelines for grant applicants, during the programme launching conference organised by the MA, during the partnership forums and during the information sessions, in 2016. - trainings / technical meetings for programme management structures on various topics, between 2014-2017: - MA and JTS - please see below the status of implementation under Human resources risk; - AA - development and set up of the management and control systems, programme audit. - programme website, social media page and communication materials (leaflets, newsletter) used/distributed for the dissemination of information on the programme and of the first call for proposals. - MA and JTS programme working procedures drawn up taking into account the ENI CBC legal framework. | Active
| Programme implementation risks | Calls for proposals reach relevant stakeholders in all participating countries | Decreasing interest from applicants in ENI CBC because of lengthy procedures for selection/contracting and grant payment | 2015 | JPC | Lengthy procedures for selection/contracting and grant payment | 1 | 1 | 3 | 0.33333 | More efficient and timely procedures are put in place | 1 | 1 | 3 | 0.33333 | MA, JTS, JMC | 2017-1st call 2018-2nd call | The provisions included in the Guidelines for Grant Applicants and its annexes for the first call for proposals have used the lessons learnt of the 2007-2013 programming period. The interest of the applicants was shown by the high number of applications submitted. | Solved-1st call Active-2nd call
| Programme implementation risks | Calls for proposals reach relevant stakeholders in all participating countries | Difficulties in finding partners limits countries balanced participation in the programme | 2015 | JPC | Limited capacity (organisational, financial) for partners search and partnership establishment | 2 | 1 | 2 | 1 | Provide improved partner search tools and opportunities | 1 | 1 | 2 | 0.5 | MA, JTS, NA | 2017-1st call 2018-2nd call | 2 partnership forums were organised by TESIM (EU funded project - Technical support to the implementation and management of ENI CBC programme) and MA in 2016. The participation of potential applicants from all participating countries in the programme were invited to the forums and TESIM covered the costs for some of the organisations from all the countries. The programme website contains a section dedicated to finding partners. This tool will be able to be used for the second call for project proposals as well. | Solved-1st call Active-2nd call
| Programme implementation risks | Beneficiaries have adequate technical & financial capacity for project implementation | Limited capacity (including financial) of project partners hampers project implementation | 2015 | JPC | Limited capacity (including financial) of project partners | 2 | 1 | 2 | 1 | Communication is strengthened and additional trainings are provided to enhance project management capacity of partners, project co-financing and adequate pre-financing issues are addressed if necessary | 2 | 1 | 2 | 1 | MA, JTS, NA, JMC | permanent | The grant payment arrangements, already published together with the guidelines for grant applicants under the first call for proposals, take into account the lessons learnt of the 2007-2013 programme and it is expected that the increased threshold for the prefinancing payment will be in the advantage of the beneficiaries. The provision of cofinancing from the state budget is to be agreed by the national authorities at programme level. Trainings to the project beneficiaries are to be organised by the JTS after the signing of the grant contracts. | Active
| Programme implementation risks | Beneficiaries implement the project activities as planned, without interruptions caused by lenghty payment procedures | Projects partners face implementation difficulties because of slow grant payment procedures | 2015 | JPC | Slow grant payment procedures | 2 | 2 | 3 | 1.3333 | Procedures are revised and improved | 2 | 2 | 3 | 1.3333 | MA, JTS, NA, CCP | permanent | The procedures related to the approval of the project reports, which influence the grant payments schedule (expenditure verification - under preparation, monitoring, authorising), will use / have used the lessons learnt of the 2007-2013 programming period and will take into account the use of eMS, which is expected to facilitate the processes. | Active
| Programme implementation risks | Beneficiaries (of projects and TA) implement the projects in accordance with the programme rules, EU and national law | Financial losses at programme level resulting from fraud or financial mismanagement | 2015 | JPC | Fraud or financial mismanagement | 2 | 1 | 2 | 1 | Monitor and ensure that anti-fraud mechanisms put in place and programme audit and control measures function effectively, improve them as necessary | 2 | 1 | 2 | 1 | MA, AA, JTS, NA, EC | permanent | The programme procedure for risk management and anti-fraud measures is approved and the first exercise for fraud risks is summarised in the table below. The procedures for management of irregularities, including fraud, which engage all the programme bodies, including the National Authorities, are described in the DMCS. The National Authorities will be consulted about the fraud risks and anti-fraud measures identified at programme level on the occasion of the JMC meetings. | Active
| Programme implementation risks | Projects are awarded in due time for implementation according to the deadline set | The evaluation and selection of the submitted applications do not follow the schedule envisaged for this process, with impact on the following processes (project contracting and implementation) | 2017 | MA | The JTS and MA are understaffed | 2 | 3 | 2 | 3 | Carrying out/finalisation of the employment procedures, in order to fill in the vacant positions. | 2 | 3 | 2 | 3 | SERDA, MA, MRDPAEF | permanent | Please see below the status for the Human resources risk (IV). | Active
[6 empty] | The NAs representatives do not follow the schedule set for eligibility check | 2 | 3 | 2 | 3 | Inform and request support from the NAs | 2 | 3 | 2 | 3 | JTS | 2017-1st call 2018-2nd call | The evaluation process of the applications submitted under the first call for proposals started in June 2017. Currently, the delays reported were notified to the concerned NA. | Active
[6 empty] | The selected external evaluators do not follow the schedule for evaluation/do not perform at the expected quality standards | 2 | 3 | 2 | 3 | Training sessions dedicated to the external evaluators. Regular reporting on the evaluation and selection process. Constant monitoring of the services contract for external evaluators. | 2 | 3 | 2 | 3 | JTS, SERDA | 2017-12-01 | The contracting of services / short-term hiring of external evaluators is under development. | Active
| Programme implementation risks | Projects are contracted in due time for implementation according to the deadline set | The contracting of the awarded projects do not follow the schedule envisaged for this process, with impact on the following processes (project implementation) | 2017 | MA | The JTS and MA are understaffed | 2 | 3 | 2 | 3 | Carrying out/finalisation of the employment procedures, in order to fill in the vacant positions. | 2 | 3 | 2 | 3 | SERDA, MA, MRDPAEF | permanent | Please see below the status for the Human resources risk (IV). | Active
II | Technological risks | Electronic monitoring system in place and functional for the programme and projects implementation | The eMS does not function properly, with impact on the programme and projects implementation. | 2015 | MA | The IT equipment is not enough/adequate. | 2 | 3 | 3 | 2 | Procurement and instalation of IT equipment. Constant monitoring of the eMS functioning, in order to timely identify the needs for supplementary procurements. | 1 | 3 | 3 | 1 | MA, MRDPAEF | permanent | The necessary IT equipment was acquired and installed in order to meet the initial identified needs. The eMS responsible persons are monitoring the functioning of the eMS and whether new IT acquisitions are necessary. | Active
|  | Electronic monitoring system in place and functional for the programme and projects implementation | The eMS is not properly adapted to the ENI CBC and BSB specificities, with impact on the eMS functionality for the programme and the projects. | 2015 | MA | The MA staff has not enough expertise in the specific IT field and in using the eMS. | 3 | 2 | 3 | 2 | Participation in training sessions organised by the eMS developer(INTERACT). Internal dissemination of the know how acquired during the training sessions. | 2 | 2 | 3 | 1.3333 | MA | permanent | The MA staff participated in training sessions organised by the eMS developer(INTERACT), between 2015 - 2017. The MA staff which participated in the eMS training sessions disseminated on-the-job the know how to the other MA staff. | Active
III | Human resources risks | Enough staff for managing the programme | The MA and JTS do not have enough staff compared with the workload, with impact on the effectiveness and eficiency of the activities carried out | 2016 | MA | The increase of the workload, as a result of managing 2 programmes (2007-2013 and 2014-2020). The fluctuation of staff. Lenghty procedures for hiring foreign staff within JTS. | 2 | 3 | 3 | 2 | Regular monitoring of the workload. Measures for ensuring the necessary number of staff/filling the vacant positions. Contracting external expertise for specific activities/hiring short-term employees. | 2 | 3 | 3 | 2 | MA, MDRAPFE, JTS, SERDA | permanent | At the MA level, there are currently 2 temporary unfilled positions, out of the 9 positions. The procedures for filling 1 position are on-going. At the JTS level, there are currently 2 unfilled positions (1 being temporary unfilled), out of the 9 positions. The procedures for filling 1 position are on-going. The contracting/short-term hiring of external technical evaluators for the first call for proposals is under development. | Active
|  | Competent staff for managing the programme | The MA and JTS staff does not have the necessary qualifications/knowledge for carrying out specific/new tasks, with impact on the accuracy, effectiveness and eficiency of the activities carried out | 2014 | MA | New legal framework for the programme, new staff, lack of participation to trainings | 2 | 2 | 3 | 1.3333 | Identification of the training needs and exchange of experience needs of staff. Participation of staff in training sessions and exchange of experience. | 2 | 2 | 3 | 1.3333 | MA, MDRAPFE, JTS, SERDA | permanent | The MA staff participated in training sessions/exchanges of experience organised by INTERACT/INTERACT ENPI/TESIM, during 2014-2017, on the following topics: monitoring and evaluation, KEEP, management and control systems, selection process and application pack, grant contract, communication and visibility, eMS, ENI CBC legal framework, state aid, contract management, irregularities, fraud and corruption, verifications by MA, monitoring internal control. The JTS staff participated in training sessions/exchanges of experience organised by TESIM/MA, during 2016-2017, on the following topics: draw up of internal working procedures; monitoring and evaluation and Management Information Systems; eMS for evaluation and contracting, DMCS, working procedures, training for potential applicants, guide for evaluation; ENI CBC legal framework, state aid, contract management, irregularities, fraud and corruption, verifications by MA, monitoring internal control, monitoring and evaluation. | Active
V | Delegated tasks risks | JTS delegated tasks are implemented in accordance with the framework agreement and subsequent contracts concluded with the JMA | The tasks delegated through the framework agreement are not carried out entirely/are carried out out poorly or with delays by the JTS, with impact on fulfilling the role of the MA in the programme implementation | 2017 | MA | The JTS does not have enough staff compared with the workload. The JTS staff does not have the necessary qualifications/knowledge for carrying out specific/new tasks. The procedures and instructions are not followed by the JTS staff. | 2 | 3 | 2 | 3 | Regular monitoring of the workload. Measures for ensuring the necessary number of staff/filling the vacant positions. | 2 | 3 | 2 | 3 | JTS, SERDA | permanent | Please see above the status for the Human resources risk. | Active
Identification of the training needs and exchange of experience needs of staff. Participation of staff in training sessions and exchange of experience.
[11 empty] | Constant monitoring and regular checks, including on-the-spot, by the MA of the way the JTS carries out the delegated tasks. |  |  |  |  | MA |  | The MA is monitoring/checking the JTS activities/documents, when needed. The MA will also perfom an annual check of the JTS activity.
Fraud risks
No. crt. | Category | Objectives/activities | Description of fraud risk and its impact | Date of identification | Who identified (structure) | Causes | Inherent risk |  |  |  | Preventive actions (antifraud measures) | Residual risk |  |  |  | Responsible person / structure | Deadline | Status of implementation | Active / solved / inactive risk
[7 empty] | Probability | Impact | Control capacity | Global risk evaluation (R) |  | Probability | Impact | Control capacity | Global risk evaluation (R)
[7 empty] | P | I | C | R=IxP/C |  | P | I | C | R=IxP/C
I | Evaluation and selection of applications and contracting of projects | Evaluation and selection of applications and contracting of projects without any suspicion of fraud | Attempts of influencing the selection committee | 2017 | MA | Obtaining EU financing | 1 | 3 | 3 | 1 | Limiting contacts between the selection committee and the applicants. Signature of declarations of impartiality and confidentiality by the staff involved in the evaluation and selection process. | 1 | 3 | 3 | 1 | MA, JTS, NA | permanent | The Guidelines for evaluation and selection of applications stipulate that only the president of the selection committee communicates with the applicants. The MA and JTS staff involved in the evaluation and selection process signed declarations of impartiality and confidentiality. | Active
II | Monitoring and implementation of projects | The fraud risk management exercise for these processes will be carried out according with the stages of programme implementation.
III | Expenditure verification and payment authorisation
IV | Public procurement by the beneficiaries of technical assistance (MA, JTS, AA) | Public procurement without any suspicion of fraud | The public procurement rules are not followed and the implementation of the public procurement contacts does not follow the contractual provisions, in order to benefit from personal advantages | 2017 | MA | Obtaining EU financing | 1 | 3 | 3 | 1 | Participation of staff in training sessions related to fraud, corruption and conflict of interests. Monitoring of the division of tasks when modifying procedures. Reporting to competent authorities in case of corruption. | 1 | 3 | 3 | 1 | MA, JTS, MRDPAEF, SERDA, AA | permanent | The MA staff participated in training sessions organised by MRDPAEF/other MAs/TESIM, in 2015 and 2017, on the following topics: conflict of interests; anticorruption; irregularities, fraud and corruption. The JTS staff participated in training sessions organised by TESIM, in 2017, on the following topics: irregularities, fraud and corruption. The MRDPAEF regulation for organisation and functioning and the programme procedures take into account the division of tasks and multiple layers of control. | Active
LEGEND
| Probability | Control capacity at managerial level
| Probable presence - 3 | High - 3
| Possible presence - 2 | Reasonable - 2
| Not very probable presence - 1 | Very low - 1
| Intocmit: | Mihaela CRISTINA | Manager public, SAM BMN, DGCTE
| Avizat: | Laura BOBÂRNAC | Șef serviciu Serviciul Autoritatea de Management Bazinul Mării Negre, DGCTE
|  | Eugenia STANCIU | Consilier evaluare-examinare, SAM BMN, DGCTE
|  | Alexandra CALOTIȚĂ | Șef serviciu Serviciul Monitorizare Proiecte, DGCTE
|  | Irina MUREȘAN | Șef serviciu Serviciul Autorizare Proiecte, DGCTE
|  | Cornelia PARASCHIV | Consilier CNRC, DGCTE
|  | Elena BUNGĂRDEAN | Consilier CNRC, DGCTE
|  | Mihaela BÎȘCĂ | Șef serviciu Serviciul Anticorupție, Direcția Integritate, Bună Guvernare și Politici Publice
| Aprobat: | Iulia HERTZOG | Șef AM

## JTS Risks Registry
| MINISTRY OF REGIONAL DEVELOPMENT, PUBLIC ADMINISTRATION AND EUROPEAN FUNDS MA Black Sea Basin Unit |  |  | OPERATIONAL PROCEDURE |  |  |  | Code: PO.DAM-PCTE.BMN.11
[8 empty] | Edition I |  | Revision 0
|  |  |  | Procedure for risk management and identification of antifraud measures for the Joint Operational Programme Black Sea Basin 2014-2020 |  |  |  | Page 1
Risk Matrix template
Date of issue: xx.xx.20xx
No. crt. | Category | Objectives | Description of the event | Description of its impact if the event occurs | Date of identification (year) | Who identified (structure) | Source | Inherent risk |  |  | Existing controls | Additional mitigating actions | Residual risk |  |  | Risk owner (structure & position) | Monitoring priority | Monitoring frequency (monthly/quarterly/annually) | Status of implementation | Active / solved / inactive risk
[8 empty] | Probability | Impact | Global risk evaluation (R) |  |  | Probability | Impact | Global risk evaluation (R)
[8 empty] | P | I | R=IxP |  |  | P | I | R=IxP
I | Operational | [8 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
II | Compliance | [8 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
III | Reporting | [8 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
LEGEND
| Risk | Probability/Likelihood | Consequence/Impact | Monitoring priority
| High 7 to 9 | Likely - 3 | Significant - 3 | High
| Medium 4 to 6 | Possible - 2 | Moderate - 2 | Medium
| Low 1 to 3 | Unlikely - 1 | Minor - 1 | Low
Prepared by:
Aproved by: