## Risks Registry
MINISTRY OF REGIONAL DEVELOPMENT, PUBLIC ADMINISTRATION AND EUROPEAN FUNDS MA Black Sea Basin Unit |  | OPERATIONAL PROCEDURE |  |  |  | Code: PO.DAM-PCTE.BMN.11
[6 empty] | Edition I |  |  | Revision 0
|  | Procedure for risk management and identification of antifraud measures for the Joint Operational Programme Black Sea Basin 2014-2020 |  |  |  | Page 1
Risk register Armenia - ENI CBC Black Sea Basin 2014-2020
Date of issue: 15.05.2018
Category | Objectives/activities | Description of risk and its impact | Date of identification | Who identified (structure) | Causes | Inherent risk |  |  |  | Preventive actions | Residual risk |  |  |  | Responsible person / structure | Deadline | Status of implementation | Active / solved / inactive risk
[6 empty] | Probability | Impact | Control capacity | Global risk evaluation (R) |  | Probability | Impact | Control capacity | Global risk evaluation (R)
[6 empty] | P | I | C | R=IxP/C |  | P | I | C | R=IxP/C
Programme participation | To increase participation of AM institutions in awarded project | Low participation, due to lack of adequate knowledge and understanding of the EU opportunities | 2018 | NA/CCP | Lack of experience (not many EU projects in AM) & inexistence of consolidated networks of partners with institutions from other countries, compared to other participating countries | 3 | 3 | 2 | 4.5 | Carry out problem analysis (why it happenned); better targeted events; guidance in national and programme languages; partner forum in Yerevan with strong preparation; more coordination with the other NAs | 2 | 3 | 2 | 3 | NA | End of next call | Partner forum and events already agreed with MA, with TESIM support | Active
Compliance | To ensure adequate reliability of EVR | irregularities not detected by controllers | 2018 | NA/CCP/MA | Lack of experience and knowledge of the controllers | 2 | 3 | 2 | 3 | Set up a long list of controllers; deliver training, together with MA & TESIM; support to controllers | 1 | 2 | 2 | 1 | CCP | permanent | Procedures for long list under development | Active
LEGEND
Probability | Control capacity at managerial level
Probable presence - 3 | High - 3
Possible presence - 2 | Reasonable - 2
Not very probable presence - 1 | Very low - 1
Intocmit: | Raluca LEVIȚSCHI | Manager public, SAM BMN, DGCTE
Avizat: | Ana-Lucia GHEORGHE | Șef serviciu Serviciul Autoritatea de Management Bazinul Mării Negre, DGCTE
| Dana ONOFREI | Consilier evaluare-examinare, SAM BMN, DGCTE
| Alexandra CALOTIȚĂ | Sef serviciu Serviciul Monitorizare Proiecte, DGCTE
| Mihai GORIE | Consilier Serviciul Monitorizare Proiecte, DGCTE
| Irina MUREȘAN | Șef serviciu Serviciul Autorizare Proiecte, DGCTE
| Cornelia PARASCHIV | Consilier CNRC, DGCTE
| Georgeta DINA | Consilier, Serviciul Anticorupție, Direcția Integritate, Bună Guvernare și Politici Publice
| Andreea GRIGORE | Director, Direcția Integritate, Bună Guvernare și Politici Publice
Aprobat: | Iulia HERTZOG | Șef AM