## Full1
PROCUREMENT PLAN
Project name | CASE CBC
Project duration | 30 months
Lead beneficiary
Nature | Description | Type of procurement procedure | Launch of procedure | Award | End of contract | Amount in Euro
Works | Partial adaptation of hospital annexed building as laboratory | Open tender | Q3Y1 | Q4Y1 | Q4Y2 | 400000
Supplies | Laboratory equipment | Open tender | Q2Y2 | Q3Y2 | Q4Y2 | 200000
Services | Logistics for launching event (hotel, catering, etc.) | Direct award | Q1Y1 | Q1Y1 | Q1Y1 | 2500
Services | Interpreters for launching event | Direct award | Q1Y1 | Q1Y1 | Q1Y1 | 1000
Services | Logistics for training event | Direct award | Q4Y2 | Q1Y3 | Q1Y3 | 2000
Services | Interpreters for launching event | Direct award | Q4Y2 | Q1Y3 | Q1Y3 | 1000
Services | Trainers | Direct award | Q4Y2 | Q1Y3 | Q1Y3 | 3000 | 9500 | 1.531%
Services | Accommodation for researches in exchange stage | Direct award | Q2Y2 | Q3Y2 | Q1Y3 | 11000
620500
Beneficiary
Nature | Description | Type of procurement procedure | Launch of procedure | Award | End of contract | Amount in Euro
Works | Partial adaptation laboratory | Open tender | Q3Y1 | Q4Y1 | Q4Y2 | 100000
Supplies | Laboratory equipment | Open tender | Q2Y2 | Q3Y2 | Q4Y2 | 175000
Services | Logistics for closing event (hotel, catering, etc.) | Direct award | Q1Y1 | Q1Y1 | Q1Y1 | 2500
Services | Interpreters for launching event | Direct award | Q1Y1 | Q1Y1 | Q1Y1 | 1000
Services | Logistics for training event | Direct award | Q4Y2 | Q1Y3 | Q1Y3 | 2000
Services | Interpreters for launching event | Direct award | Q4Y2 | Q1Y3 | Q1Y3 | 1000
Services | Trainers | Direct award | Q4Y2 | Q1Y3 | Q1Y3 | 3000 | 9500 | 2.964%
Services | Accommodation for researches in exchange stage | Direct award | Q2Y2 | Q3Y2 | Q1Y3 | 11000
Services | Field work for research | Direct award | Q3Y1 | Q4Y1 | Q1Y2 | 25000
320500