## risk profile
RISK PROFILES OF THE PROJECT AND BENEFICIARIES
Project name | CASE-CBC
Project Lead beneficiary | Municipality of Lugo (Member State)
Beneficiaries | Foundation for cancer research (Partner Country)
General remarks | A successful project was managed by the same partners in 2014-2020 period
Inherent risks - risks associated with the project
Risks factors (risk of irregularities) | Applicable to the project | Detailed information | Score (1 to 4) | (1 - low risk 2 - medium risk 3 - high risk 4 - very high risk)
Significant budget | Yes | Project budget over 1.5 M€ | 3
Large partnership | No |  | 1
Large public procurement(s) | Yes | One infrastructure procurement and laboratory equipment by the Foundation and works in a hospital by the municipality | 3
Use of simplified cost option | Yes | Staff, travel costs and indirect costs are financed through SCOs. Works, equipment and expertise is financed through actual costs | 2
Significant number of outputs | No | On top of the infrastructure, the project has a limited numer of soft activities: one joint research, two events and two trainings | 1
Few or insufficient evidence can be provided after completion of the project | Yes | Evidence of the works and equipment can be easily provided. The soft activities can be documented | 1
Overall project risk profile |  |  | 1.8333
Inherent risks - risks associated with the Lead Beneficiary
Risks factors (risk of irregularities) | Applicable to the project | Detailed information | Score (1 to 4)
Legal status | Yes | Local administration | 1
Experienced beneficiary | Yes | This institution successfully implemented a project in the previous period in the same field. It has long experience in ERDF mainstream | 1
Conflict of interest | Yes | All staff adhered to the Code of Ethics and there are solid procedures for the management of potential conflict of interest | 2
Capacity to implement | Yes | The staff of the municipality has long experience in the type of investment to be financed. However, the only experience in CBC projects is the one in the previous period | 2
Double funding risk | Yes | Infrastructure might be financed also with mainstream funds. | 1
Grant dependency | Yes | The annualised size of the grant is less than 5% of the annual budget of the institution | 2
Number of projects implemented by the beneficiary | No | This is the only project currently under implementation | 1
Overall risk profile of the Lead Beneficiary |  |  | 1.4286
Inherent risks - risks associated with the Beneficiary
Risks factors (risk of irregularities) | Applicable to the project | Detailed information | Score (1 to 4)
Legal status | Yes | Private foundation with some public institutions in the board (30% of the board members) | 2
Experienced beneficiary | Yes | This institution successfully implemented a project in the previous period in the same field. It has long experience in Horizon Europe | 1
Conflict of interest | Yes | There is a Code of Ethics in the website, but no evidence of the adhesion by the staff. To the best knowledge of JS, there is no written procedures for the management of potential conflict of interest. | 3
Capacity to implement | Yes | The staff of the foundation has long experience in the project management, including the type of activity financed by this project | 1
Double funding risk | Yes | Research and other soft activities might be financed by Horizon Europe | 3
Grant dependency | Yes | The annualised size of the grant is 35% of the annual budget of the institution | 3
Number of projects implemented by the beneficiary | Yes | The institution is currently implementing 4 more EU-financed projects | 3
Overall risk profile of the Lead Beneficiary |  |  | 2.2857